## Sheet1
Shakthivel | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing a part of UI Wireframes, Update Sprint Journal
|  | What am I planning to do to next? | Revise the UI Wireframes and start the Front End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Revised and made changes in UI Wireframes and started Front End Development, Update Sprint Journal
|  | What am I planning to do to next? | Start building user interface for Landing, Signup, Login Pages
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Finished building user interface for Landing, Signup, Login Pages, Update Sprint Journal
|  | What am I planning to do to next? | Start building user interface for Dashboard, Booking Flights and Integration of Login and Signup with Backend
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of Signup and Login
| Sprint 4 | What task did I work on/complete? | Integrated Signup and Login with Backend APIs and Completed UI for Dashboard, Search Flight, Book Flight
|  | What am I planning to do to next? | Integrating Dashboard, Search Flight, Book Flight with Backend APIs and Start building UI for Update Reservation
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of Dashboard, Search Flight, Book Flight
| Sprint 5 | What task did I work on/complete? | Integrated Dashboard, Search Flight, Book Flight with Backend API and Completed UI for Update Reservation
|  | What am I planning to do to next? | Integrating Update Reservation With Backend API and Start building UI for Cancel Reservation and Travel History
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of Update Reservation
| Sprint 6 | What task did I work on/complete? | Integrated Update Reservation With Backend API and Completed UI for Cancel Reservation and Travel History
|  | What am I planning to do to next? | Integrating Cancel Reservation with Travel History and Deploying React Application, Documentation
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of Cancel Reservation
| Sprint 7 | What task did I work on/complete? | Integrated Cancel Reservation and Travel History with Backend APIs and Deployed React Application
What am I planning to do to next?
What tasks are blocked waiting on another team member?
Shravan | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing a part of the system architecture, getting started with the githhub projects tool(similar to trello to and JIRA)
|  | What am I planning to do to next? | Revise the system architecture and start the Back End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Revised the system architecture and started the Back End Development, plan user stories for the team
|  | What am I planning to do to next? | Start building backend functionalities of Login and singup for employee
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Login and Signup APIs for Airline Employee, Involved in DB design,
|  | What am I planning to do to next? | The rest of APIs for employee page and do some APIs on customer end as well
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Create EditFlight, AddFlight route API, Cancel a flight in a particular route, create user stories for sprint 4, peer review
|  | What am I planning to do to next? | Get Available Seats, Get Upcoming flight for employee,
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Get Available Seats, Get Upcoming flight for employee, functional testing of the APIs done so far.
|  | What am I planning to do to next? | Create Change seat API, Get All Reservation API, Express Validation For Node
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Create Change seat API, Get All Reservation API, Express Validation For Node, functional testing
|  | What am I planning to do to next? | Get Upcoming Customer Reservations, Get Completed Customer Flights, functional testing
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | Get Upcoming Customer Reservations, Get Completed Customer Flights, Peer review, updated readme with design decisions and feature sets, create getCompletedCustomerFlights, getUpcomingCustomerReservations
|  | What am I planning to do to next? | End of Sprints
|  | What tasks are blocked waiting on another team member? | None
Divya | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing a part of the system architecture, Burndown chart
|  | What am I planning to do to next? | Revise the system architecture and start the Back End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Revised the system architecture and started the Back End Development, Burndown chart
|  | What am I planning to do to next? | Backend Setup and Start building backend functionalities of Signup
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Finished Backend Setup and Started building backend functionalities of Signup, Burndown chart
|  | What am I planning to do to next? | Revise System Architecture, Create Book FLight API, Search Flight API, Burndown chart
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Revise System Architecture, Create Book FLight API, Search Flight API, Burndown chart
|  | What am I planning to do to next? | Burndown chart
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | API testing for Book FLight and Search Flight, Burndown chart
|  | What am I planning to do to next? | Cancel reservation API, Express Validation for Node API, Integrate , Burndown chart
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Cancel reservation API, Express Validation for Node API, Integrate , Burndown chart
|  | What am I planning to do to next? | Deployment of Application on Cloud, Burndown chart, Peer review
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | Deployment of Application on Cloud, Burndown chart, Peer review
What am I planning to do to next?
|  | What tasks are blocked waiting on another team member? | None
Saurabh | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing a part of UI Wireframes, Update Weekly scrum report
|  | What am I planning to do to next? | Revise the UI Wireframes and start the Front End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Revised the UI Wireframes and started the Front End Development, Update Weekly scrum report
|  | What am I planning to do to next? | Start building user interface for Profile Page
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Completed the UI for the Profile page, Update Weekly scrum report
|  | What am I planning to do to next? | Integrate ProfilePage with backend and update the Profile button functionality
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of Profile Page
| Sprint 4 | What task did I work on/complete? | Profile page integration with backend, Update Weekly scrum report
|  | What am I planning to do to next? | Employee login and dashboard
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Employee login and Dashboard and its testing, Manage Flight Design and implement, Update Weekly scrum report
|  | What am I planning to do to next? | Add Flight, Edit Flight, Cancel Flight UI at Front End and its integration
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Integration of Add Flight, Edit Flight and Cancel Flight with Backend, Update Weekly scrum report
|  | What am I planning to do to next? | Front testing and Deployment on cloud
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | End to End testing, Peer review, Deployment on cloud, Documentation
What am I planning to do to next?
|  | What tasks are blocked waiting on another team member? | None