## Scrum Report
|  |  |  | Week #1 (15 hrs / week) | [6 empty] | Week #2 (15 hrs / week) | [6 empty] | Week #3 (15 hrs / week) | [6 empty] | Week #4 (15 hrs / week) | [6 empty] | Week #5 (15 hrs / week) | [6 empty] | Week #6 (15 hrs / week) | [6 empty] | Week #7 (15 hrs / week)
Backlog Item | Task | Task Owners | Initial Estimate (Total Sprint Hours = 60 x 7) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49
 | time axis 2014-10-18 to 2014-12-05
|  |  | 420 | 411 | 402 | 393 | 384 | 375 | 366 | 357 | 348 | 339 | 330 | 321 | 312 | 303 | 294 | 285 | 276 | 267 | 258 | 249 | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123 | 114 | 105 | 96 | 87 | 78 | 69 | 60 | 51 | 42 | 33 | 24 | 15 | 6 | -3 | -12 | -21
|  |  | 420 | 420 | 420 | 400 | 400 | 380 | 360 | 360 | 360 | 340 | 340 | 320 | 320 | 300 | 300 | 300 | 280 | 280 | 260 | 260 | 240 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Planning & Design Discussions | Discussing and finalizing Technology Stack | Divya | 105 | 2014-10-18: 105; 2014-10-19: 105; 2014-10-20: 100; 2014-10-21: 100; 2014-10-22: 95; 2014-10-23: 90; 2014-10-24: 90
| Architecture Diagram | Shakthivel | 105 | 2014-10-18: 105; 2014-10-19: 105; 2014-10-20: 100; 2014-10-21: 100; 2014-10-22: 95; 2014-10-23: 90; 2014-10-24: 90
| Sprint Journal | Saurabh | 105 | 2014-10-18: 105; 2014-10-19: 105; 2014-10-20: 100; 2014-10-21: 100; 2014-10-22: 95; 2014-10-23: 90; 2014-10-24: 90
| Scrum Report | Shravan | 105 | 2014-10-18: 105; 2014-10-19: 105; 2014-10-20: 100; 2014-10-21: 100; 2014-10-22: 95; 2014-10-23: 90; 2014-10-24: 90
Sprint Planning
Functionalities Planning
UI Wireframe
Code Setup | Revising UI Wireframes, System Architecture | Divya |  | 2014-10-25: 90; 2014-10-26: 85; 2014-10-27: 85; 2014-10-28: 80; 2014-10-29: 80; 2014-10-30: 75; 2014-10-31: 75
| Start user interface for Landing, Signup, Login Pages, Profile page | Shakthivel |  | 2014-10-25: 90; 2014-10-26: 85; 2014-10-27: 85; 2014-10-28: 80; 2014-10-29: 80; 2014-10-30: 75; 2014-10-31: 75
| Start Backend Setup | Saurabh |  | 2014-10-25: 90; 2014-10-26: 85; 2014-10-27: 85; 2014-10-28: 80; 2014-10-29: 80; 2014-10-30: 75; 2014-10-31: 75
| Start Backend Functionalities of Login and Signup | Shravan |  | 2014-10-25: 90; 2014-10-26: 85; 2014-10-27: 85; 2014-10-28: 80; 2014-10-29: 80; 2014-10-30: 75; 2014-10-31: 75
Update Sprint Journal, Sprint Report
| Complete user interface for Landing, Signup, Login and Profile Pages | Divya |  | 2014-11-01: 75; 2014-11-02: 70; 2014-11-03: 70; 2014-11-04: 65; 2014-11-05: 65; 2014-11-06: 60; 2014-11-07: 60
| Start building user interface for Dashboard, Booking Flights | Shakthivel |  | 2014-11-01: 75; 2014-11-02: 70; 2014-11-03: 70; 2014-11-04: 65; 2014-11-05: 65; 2014-11-06: 60; 2014-11-07: 60
| Start Login and Signup APIs for Airline Employee | Saurabh |  | 2014-11-01: 75; 2014-11-02: 70; 2014-11-03: 70; 2014-11-04: 65; 2014-11-05: 65; 2014-11-06: 60; 2014-11-07: 60
| The rest of APIs for employee page and some APIs on customer end | Shravan |  | 2014-11-01: 75; 2014-11-02: 70; 2014-11-03: 70; 2014-11-04: 65; 2014-11-05: 65; 2014-11-06: 60; 2014-11-07: 60
Complete Backend Setup
Start Backend functionalities of Signup
Update Sprint Journal, Sprint Report
| Create Add Flight route API | Divya
| Create EditFlight route API | Shakthivel
| Cancel a flight in a particular route | Saurabh
| Integrate login, signup, profile pages with backend | Shravan
Peer review of the work doen so far
Functional testing backend and frontend
| Create search and book flight API | Divya
Shakthivel
Saurabh
Shravan
Divya
Shakthivel
Saurabh
Shravan
Divya
Shakthivel
Saurabh
Shravan
Team:
Shravan | 15 hours / Week
Divya | 15 hours / Week
Shakthivel | 15 hours / Week
Saurabh | 15 hours / Week
Total Available Hours During Sprint: | 420

## Burndown Chart
Sprint 1
Calender Day | Planned | Actual
2021-10-17 | 60 | 60
2021-10-18 | 48 | 60
2021-10-19 | 40 | 40
2021-10-20 | 32 | 40
2021-10-21 | 24 | 20
2021-10-22 | 18 | 20
2021-10-23 | 8 | 0
Sprint 2
Calender Day | Planned | Actual
2021-10-24 | 60 | 60
2021-10-25 | 48 | 40
2021-10-26 | 40 | 40
2021-10-27 | 32 | 20
2021-10-28 | 24 | 20
2021-10-29 | 18 | 0
2021-10-30 | 8 | 0
Sprint 3
Calender Day | Planned | Actual
2021-10-31 | 60 | 60
2021-11-01 | 48 | 40
2021-11-02 | 40 | 40
2021-11-03 | 32 | 20
2021-11-04 | 24 | 20
2021-11-05 | 18 | 0
2021-11-06 | 8 | 0